## Readiness & Transition Log
ID | Issue / Dependency | Category | Required Action | Owner | Status | Blocks Issue? | Closure Evidence / Decision
GR-001 | Master IMS approval architecture is not yet aligned with the intended CDI domain-based approval route. | Governance dependency | Resolve governing approval architecture in Master IMS and confirm CDI approval route before issue. | CCO / MD-CEO | Open | Yes | Approved Master IMS / formal governance decision.
GR-002 | Legacy retention policies are being retired as active instruments; their substantive rules still require Record Name-level migration and reconciliation. | Retention authority | Preserve legacy rule lineage; validate each applicable rule by authority/context; approve the successor rule in the Catalogue/Retention View; then close the migration. | Compliance / DPO / Legal as applicable | Policy retirement decided / rule migration open | No - control family; Yes - final Retention View | Approved retention authority mapping and conflict closures.
GR-003 | Document Authoring Guide is to be retired into CDI. | Document retirement | Confirm all enduring authoring, automated-evidence and GRC-readiness rules are represented in CDI; then mark the Guide superseded/retired. | Compliance | Ready to retire on CDI issue | Yes - CDI issue action | Issued CDI revision history and Document Register retirement entry.
GR-004 | Compliance Monitoring Procedure is to be retired after migration of generic principles. | Document retirement | Confirm no unique service-specific operational requirement is orphaned; migrate/reassign any such content; retire the Procedure. | Compliance | Ready to retire on CDI issue subject to unique-content check | Yes - CDI issue action | Issued CDI plus Document Register retirement entry and any successor operational reference.
GR-005 | Discovery population contains approximately 604 candidate Record Names and many aliases/duplicates. | Catalogue regularisation | Canonicalise Record Names and assign stable Record IDs before approval. | Records Governance / Process Owners | Open | No - CDI; Yes - Catalogue release | Approved Enterprise Records Catalogue.
GR-006 | Discovery source labels include a very large number of provisional Record Type labels. | Taxonomy regularisation | Map candidates to the controlled taxonomy; merge synonyms; approve only genuine semantic gaps through extension process. | Records Governance | Open | Yes - taxonomy release | Approved Record Type Taxonomy.
GR-007 | Findability metadata is incomplete for many candidate Record Names. | Findability | Validate authoritative source/location, retrieval instruction and context-specific custodian. | Process Owners / Custodians | Open | Yes - Findability View | Validated Findability View.
GR-008 | Retention/disposition metadata is incomplete or locally inconsistent for many candidate Record Names. | Retention / disposition | Validate period/rule, trigger, authority, disposition, destruction method/evidence and hold treatment. | Compliance / Specialist Authorities | Open | Yes - Retention View | Validated Retention & Disposition View.
GR-009 | Discovery tracker contains known copy-forward contamination in selected Access Control and Testing rows. | Source quality | Do not promote contaminated rows as canonical evidence; re-verify only if a candidate from those rows is needed during canonicalisation. | Records Governance | Controlled exception | No | Validation note / source recheck where used.
GR-010 | Verification SOP references a Verification Data Retention Schedule that has not yet been located/reconciled. | Referenced source | Locate and assess the schedule, or formally determine that it is obsolete/uncontrolled and reconcile the governing retention rules. | Verification / Compliance | Open | Yes - affected records | Located source and approved reconciliation decision.
GR-011 | Legacy standalone retention policies to be retired as active governance instruments on successor issue. | Document retirement | Update Document Register / controlled-document status; retain source lineage for individual retention rules until migration closes. | Compliance | Planned on issue | No | Retirement entries plus approved successor family.
GR-012 | AI/GRC drafting must not dead-end where an authoritative managed object is missing. | GRC operating rule | Implement 'authoritative reference first; governed extension where necessary' in drafting/checker prompts and workflows. Provisional objects route to the applicable governance owner. | Compliance / GRC Owner | Rule defined | No | Updated agent instructions / validation rules.

## Control Family Principles
Principle | Rule
Control documents are enduring | Temporary blockers, live conflict narration and project-status commentary live in readiness/transition records, not permanent controls.
Record Type defines semantics | Record Type does not define custodian, findability, retention, disposition or destruction.
Record Name carries governance | Operational governance attaches to the governed Record Name in its applicable process/control context.
Taxonomy is controlled | The current taxonomy is exhaustive for authorised use and extensible only through controlled exception.
One record of truth | Multiple views may reference one source item; they do not create competing masters.
Specialist authority survives | Privacy, classification, lifecycle, legal/regulatory and other specialist masters are referenced rather than duplicated.
Authoritative reference first; governed extension where necessary | Reuse the authoritative object where it exists. If a genuine gap is discovered, propose and route the new/amended object through its governance process; drafting need not stop while the proposal remains clearly provisional.